## Sheet1
As of now, these numbers are estimations. I encourage each member to add tasks and modify numbers for their tasks as needed.

Color Chart		Task	Week 1	Week 2	Week 3	Week 4	Week 5
Allan	(Turquoise 2)			Estimated time to complete tasks will be listed inside the cell
Aykut	(Yellow 5)	Establish Communication & Filesharing		* ? *
Brian	(Red 5)	Create GDD, TDD, Art & Style Guide	5 each
Charles	(Magenta 4)	Create Art Assets	* Update assets as needed
Shaun	(Light Green)	** Player Ship		1
Multiple People	(Gray 40%)	** Terrain		2
Task Complete	(White on Black)	** Projectiles		1
LATE		** Shields			1
** = Subtask		** Bubble Jets			1
		** Boss # 1		1
		** Boss # 2			1
		** Boss # 3				1
		** Enemies 1 - 2		2
		** Enemies 3 – 4			2
		** Background(s)		1	1	1
		** Power-ups			1	1
		** Implosion Animations			3	3
		Create Levels ( 1 per week)
		** Initial Level Concept (Due Fridays)		3
		** Level Implementation
		** Camera Flow		10	4	4
		** Sprite & Spawn Locations		5	5	5
		Player Controls	2
		Artificial Intelligence	* Update assets as needed
		** Boss # 1		8
		** Boss # 2			8
		** Boss # 3				8
		** Enemies 1 – 2		5	2
		** Enemies 3 – 4			5	2
		** Death Animation (Art provided)				2
		Collision Detection		8
		** Player & Bubbles
		** Player & Terrain
		** Player & Enemy
		** Bullet & Terrain
		** Bullet & Enemy
		Main Menu
		** Menu Design			2
		** Implementation			2
		Game Over Screen
		** Design			2
		** Implementation				1
		High Score Screen
		** Design			2
		** Implementation			5
		** Score Gains
		** Score Recording
		Prototype Due
		First Playable Due
		Alpha Due
		Beta Due
		Gold Master Due
		Play Testing		???	???	???	???

		Estimated Hour of Work	Week1	Week 2	Week 3	Week 4	Week 5
		Allan	7 + ??	8 + ??	13 + ??	5 + ??	???
		Aykut	5 + ??	13 + ??	15 + ??	12 + ??	???
		Brian	5 + ??	11 + ??	13 + ??	8 + ??	???
		Charles	5 + ??	???	6 + ??	4 + ??	???
		Shaun	5 + ??	15 + ??	11 + ??	10 + ??	???